## Sheet1
Block No.
|  |  |  | Dereje |  | Uncontracted Sale.
|  | NURU |  | Dereje |  | Uncontracted Sale.
|  | YAHYA ALIYI |  | Dereje
|  | ABDULJEBAR HUSSEN |  | Dereje
TAYECH BETEWEDED
NEJAT MOHAMMED
ASEFA HUNDE
EDRIS GIBRIL
|  | SHEMSIYA AHMED |  |  |  | Ahmed Tusa
|  | YAHYA ALIYI |  |  |  | Yahya's Residence
|  | MESERET TAFESE |  |  | Completed | Rahma hussein sold to Bekele Ashabir, Bekele sold to current owner
|  | ASRAR AGA |  |  |  | Rahma hussein sold to Asrar Aga
|  | EDAO HUSSEIN |  |  | Completed
|  | BAME EDAO |  |  | Completed
MUSTEFA USMAN
|  | NESANET HAILU | PENDING |  | 1st Slab
|  | TIGIST G/EGZIYABEHER |  |  |  | Gibril Kadi sold to current owner
|  | GEZAHEGN TESEMA | PENDING |  | G + 2 Partial Block Work, No Roof | Sileshi's Father
|  | SILESHI GEZAHEGN | PENDING |  | 1st Slab
|  | RAHMA HUSSEIN |  |  | Elevation Column Errected | In House Sale
ALEMAYEHU DAGNE ZEMARIAN
HANA MELESE GIZAW
GENET BIRHAN
YARED GETAHUN
MAMUSHET AREGAW
DANIEL TESFA
JENBERU TADESSE NADEW
DR.DANIEL TEKLE G/EGZIABHER
YOSEF MICHAEL AMBAYE
ABERA ZEWEDU TESEMA
DENNENESH GENANAW
GETU TEDLA AYELE
DR. MEKURIA AREGAW
SHEWANDAGNE SEIFU
ROMAN SEIFU AND TED WONDAGEGNEH
ETALEM DEMISE
DANIEL SAMUEL NEGASH
MEAZA W/MARIAM & GIRMA W/T
BELETE DEMISEW W
|  | TULU DIMTU REAL ESTATE |  |  |  | A land parcel that was contested in court against GALGALO BORU, later solved in negotiation.
ZEGEYE ABEBE & NIGISTE ASEFAW
SIRAKE ZEWEDE & SABA ABREHAM
HIRUT YIMERE/HAILU TADESSE
ADDISALEM W/G.&YOSEF ALEME
ESKEDAR MENGESHA
ZERIHUN MEKONNEN DAMTE
GETENET TESHOME METAFERIA
SELAMAWIT HABTE HAGOS
MERUTSE GIRMAI & LEMLEM G/HIWOTE
ROMAN ADMASU
HABTAMU ASEFA
MUNIRA ABDULLAHI
HIRUT DERESE WOLDE
AZEBE MOGESE
MENBERE FIKADE
ELENI TEKLE G/EGEZIHABERE
GIRMA NEGASH & BETHLIHEM Z.
ALEMAZ TECHANE
REBECA G/HIWOT SOLOMON
KEHASENA W/MIHRET
EWNETU ABTE & HIRUT NIGATU
NETSANET GIZAW &SEIFU W/YOHANES
HALEWIYA OSMAN SEMERAI
HIWOT ABEBE
ABERA KIDANU HABTE
SAMSON TESFAYE G/EGIZEYABHER
GETACHEW VENERA GEMARI
ALMAW BIRU CHIKUALA
GETACHEW ARAYA
FEDILA MOHAMMED REDI
MERID ADEMASU BEYENE
WELLELA HIRPHASA
ALEMAZ ABERA MAMO
SAADA ABDULLAHI ALI
LEMELEM ALEMAYEHU
AMIN JEMAL
FIKRE AMARE
FITSUM KEBEDE
ALISE PAROUNAKIAN YOHANESE
|  | TESHOME MEKETE |  | Teshome | 1st Slabd
MIHIRET SISAY
MERAWI FELEKE AND JUDITH ABEBE
DAMOZE GAMADA
YOSEF YEREGA CHEGEN
ABEBA TAFA
MOLALET TSEDEKE W/GIORGIS
SELAM DESTA KEBEDE
BIRUKTAWIT ABJE & KIRUBEL WENDOW.
MARU DHABA
|  | MIHRET DEMISSEW |  |  |  | Dr. Mekuria. Undocmented sale
TSEDALE MEKONEN &MESFIN MOTUMA
BAYAN AHMED
|  | HIRUT G/SILASE | ISSUED
AHMED KADI
|  | ABDU KASIM |  |  | Completed
|  | HUZEYFA MUSA |  |  | Completed
SADAM AHMED
FOZIYA AHMED
DAWOD ALO
TULU DIMTU REAL ESTATE
|  | AYUB OR OBSA AKOSHA | ISSUED |  | Completed
|  | RIYAD | ISSUED |  |  | Abduljelil Contractor Employee
Elevation Column Errected
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
| 200 | HUSSEIN ABUBAKAR | ISSUED
|  | KHALID ABDULREZAK AMAN |  |  |  | Sh/ Mohammed Nejib is the agent on the signed agreement
| 320 | REDWAN JEMAL IMAMU | ISSUED |  |  | Zahbiya Brother in law/ extension of few permiter on the river side.
|  | DESALEGN SISAY |  |  | Beasement + G + 1, Plastered | Raey Consultance
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
|  | SHEGAW NEGATU |  | Dereje
|  | AGA |  | Sherfedin |  | Uncontracted Sale.
|  | MARKOS |  | Teshome |  | Buyer is QATAR Resident
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
|  | TEWDROS |  | TABU
|  | TIGIST DEREJE |  | Teshome
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
|  | SEMIRA UMER |  | Sherfedin
|  | ALAMUDIN KEDIR |  | Dereje
|  | SADIK RAHMETO |  | TESHOME
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
WORKU ABERA
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
|  | ZEYTUNA ELIYASE |  | Dereje | Completed
|  | MERIA ELIYASE |  | Dereje | Completed
|  | RAMZIYA GULTA |  | Dereje | Completed. Occupied
|  | SEID IBRAHIM |  | Dereje
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
|  | KHALID MOHAMMED |  | Dereje | Completed
|  | ZUBEYDA KEDIR |  | Dereje | Completed
|  | MUDIN AHMED |  |  |  | Daime (Abdulkerim Abduro) sold to current owner
|  | MESERET SHIMEKET |  | Dereje | Completed. Occupied
|  | FATIYA ABDU |  | Dereje | Completed
|  | SHIBELAY W/MARIAM |  | Dereje | Completed. Occupied
|  | SIDIKE ABA BULBUL |  | Dereje | 1ST Slab
|  | MIFTAH |  | Sherfedin
|  | EMAN AWEL |  | Dereje | Beasement + G + 1 | Awel Buseri
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
|  | NASRE HUSSEIN |  | Dereje
|  | ABDU ABA MENCHA |  | Dereje | At Plastering Stage
|  | SADIYA ANEWAR |  | Dereje | Foundation Work
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
|  | NASREDIN ENDASHAW |  | Owner-led | Completed.Occupied
|  | ADEMEKACHEW |  | Owner-led |  | Tekiya Abduqe (Woliyii Wife) sold to current owner
|  | MUNEWAR ZEYNEDIN |  | Owner-led | Completed.Occupied
|  | GIRMA TESHOME |  | Owner-led
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
|  | TOFIK HULGAGA |  | Owner-led
|  | NEJIB ABDUKU |  | Owner-led
Owner-led
|  | ZENEBECH YAZE |  | Owner-led | Completed | Woliyi Guye Sold to Current homeowner
|  | ASIYA ABDELA & AHMED DEGDEBO |  | Owner-led
|  | MOHAMMED DEGDABO |  | Owner-led
|  | FOZIYA AMAN |  | Owner-led
|  | AYSHA BIYA |  | Owner-led
|  | YASIN UMER |  | Owner-led
|  | MOHAMMEDHUSSEIN ALIYI |  | Owner-led
|  | SOFIYA TUSE |  | Owner-led
|  | MENTESENOT FEKERE |  | Owner-led | Completed. Occupied | Previous Owner Gibril Kadi Sold to Current Homeowner
|  | ZARO |  | Owner-led | Foundation Work | Purchase rate=50,000/ Currently Under Construction
|  | SHEKURE NASRE |  | Owner-led | Completed. Occupied
|  | ABRAR AGA |  | Owner-led | Completed. Occupied
|  | SISAY KENEDY |  | Owner-led |  | Amir (Adama) sold to current homeowner
|  | AYSHA HUSSEN |  | Owner-led |  | Mohammed Edao sold to Current owner/Sold Via Amabassador Aman (3/5)
|  | NASRO ABAS |  | Owner-led
|  | BURHAN HAJI ARSE |  | Owner-led | Completed. Occupied
|  | MEZEGEBE ZELEKE |  | Owner-led | Completed. Occupied | Amir (Adama) sold to current homeowner
|  | FOZIYA HUSSEIN (YAHYA ALIYI) |  | Dereje |  | Sold to third party,but tittle is under the initial purchaser(Foziya)
|  | FOZIYA HUSSEIN (YAHYA ALIYI) |  | Dereje | Completed. Occupied | Sold to third party,but tittle is under the initial purchaser(Foziya)
TULU DIMTU REAL ESTATE
|  | MOHAMMED IBRAHIM |  | Dereje |  | The two plots are purchased by one customer; hence integrated as a single property. The land size specified on the deed is 390 SQ.Meter
|  | ADDISE SEID |  |  | Completed. Occupied
|  | TULU DIMTU REAL ESTATE |  | Dereje | Foundation Work/Floor Slab
|  | MUSEFA ABDELA |  | Dereje | Completed. Occupied
|  | TULU DIMTU REAL ESTATE |  | Sherfedin | Top tie Beam + Block Work
|  | YAHYA ALAMEREW |  | Dereje | Completed. Occupied | Previously, under Dereje Ayele(Contractor), later sold to the present owner
|  | ZEYENEBA RAHMETO |  | Sherfedin | Completed. Occupied
|  | MULUGETA DESALEGN |  | Sherfedin | Completed. Occupied
|  | TULU DIMTU REAL ESTATE |  | Sherfedin
|  | MUSTEFA H/HUSSEIN |  | Sherfedin
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
|  | BETEKA MEKETE |  | Teshome
|  | TESHOME MEKETE | ISSUED | Teshome
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE
|  | TIZITA |  | Dereje |  | Hailemichael(Finance) sold to the current tittle holder
|  | FERDOS OSMAN | ISSUED | Dereje | Occupied. At plastering Satge | Previously, under her deceased husband(Ali Mohammed, later court ruled for tittle transfer to her name.
|  | TULU DIMTU REAL ESTATE |  | Dereje
|  | MOHAMMED ABDU | ISSUED | Dereje | Completed. Occupied
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
|  | HASSEN HUSSEIN | ISSUED | Sherfedin | Completed. Occupied
|  | MOHAMMED NURE | ISSUED | Sherfedin
|  | BEDRU TEMAM | ISSUED | Sherfedin
|  | ABAS ORMANO | ISSUED | Sherfedin |  | Abas has already sold this land to third party, yet tittle is not transfered
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
|  | ABDULRAHMAN TAHIRO |  | Sherfedin
TULU DIMTU REAL ESTATE (B*)
|  | MOHAMMED | ISSUED | Sherfedin | Completed. Occupied
|  | ESMAEL MUZE | ISSUED | Sherfedin | Completed. Occupied
|  | BARAKA NASIR | ISSUED | Sherfedin | Completed. Occupied
|  | AYUB REDI |  | Sherfedin
|  | TAJUDIN SHUKRI | ISSUED | Sherfedin
|  | AHMED KEMAL |  | Sherfedin | Completed. Occupied
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
|  | DAMENECH BEGASHA |  | Dereje | On Top tie Beam
TULU DIMTU REAL ESTATE
|  | MEKEDES GIRMA |  | Dereje
TULU DIMTU REAL ESTATE (B*)
|  | RABIYA KEDIR | ISSUED | Sherfedin
|  | RABIYA KEDIR | ISSUED | Sherfedin
TULU DIMTU REAL ESTATE
|  | SHEMSIYA |  | Sherfedin
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
|  | TULU DIMTU REAL ESTATE |  | Teshome
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
|  | TOFIK SHIKUR |  | Dereje | Roofwork Underway | Split-level house with a basement
|  | HANAN AKMEL | ISSUED | Dereje |  | Abdulkerim Abduro sold this house to the current tittle holder
|  | ELIYASE AYELE | ISSUED | Dereje | Completed. Occupied | Dereje (Contractor) Brother; Split-level house with a basement
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
|  | ABDULMEJID MOHAMMED |  | MOSH
|  | NURU SETEGN |  | MOSH
|  | ABDULNEIM SHEMSU | ISSUED | Sherfedin
|  | BEDRU MUZO | ISSUED | Sherfedin
|  | MOHAMMED DELSEBO | ISSUED | Sherfedin
|  | MELIYA ASHREKA |  | Sherfedin
|  | RABI MUZEYEN | ISSUED | Sherfedin
|  | SEID KEYREDIN |  | Sherfedin
|  | BILAL DANUR |  | Sherfedin
|  | NUREDIN MOHAMMED | ISSUED | Sherfedin
|  | KEDIR TURA |  | Sherfedin
|  | HABIBA BILAL |  | Sherfedin
DELIL DINO
TULU DIMTU REAL ESTATE (B*)

## Sheet2
Tulu Dimtu Real Estate Development Inventory Sheet Zone I G+1 & Zone II G + 0 ************************************************************* Zone I G+1
Block No. | Plot No. | Plot Size (Sq.M) | Built-up Area | Purchaser Name | Title Deeds Status | Contractor | Construction Status | Remark\Comments
1 | 1 | 400 |  | Tulu Dimtu Real Estate |  | Sherfedin |  | Bare Land. Its located at the boarder edgeof the site, adjacent to the main road. At the edge of each plots a shop units are built.
| 2 | 400 |  | Tulu Dimtu Real Estate |  | Sherfedin
| 3 | 400 |  | Tulu Dimtu Real Estate |  | Sherfedin
| 4 | 400 |  | Tulu Dimtu Real Estate |  | Sherfedin
2 | 1 | 500 |  | NURU | NOT ISSUED | Dereje | At Plastering Stage | Uncontracted Sale.
| 2 | 500 |  | NURU | NOT ISSUED | Dereje | At Plastering Stage | Uncontracted Sale.
| 3 | 500 |  | YAHYA ALIYI | ISSUED | Dereje | Block Work + Roof Work
| 4 | 500 |  | ABDULJEBAR HUSSEN | ISSUED | Dereje | At Plastering Stage
| 5 | 500 |  | TAYECH BETEWEDED | ISSUED | Owner-led | Completed.Occupied
| 6 | 500 |  | NEJAT MOHAMMED | ISSUED | Owner-led | At Plastering Stage
| 7 | 500 |  | ASEFA HUNDE | ISSUED | Owner-led | Block Work + Roof Work
| 8 | 500 |  | EDRIS GIBRIL | ISSUED | Owner-led | At Plastering Stage
| 9 | 500 |  | SHEMSIYA AHMED | ISSUED | Owner-led | Completed.Occupied | Ahmed Tusa
| 10 | 500 |  | YAHYA ALIYI | ISSUED | Owner-led | Completed.Occupied | Yahya's Residence
| 11 | 500 |  | MESERET TAFESE | ISSUED | Owner-led | Completed | Rahma hussein sold to Bekele Ashabir, Bekele sold to current owner
| 12 | 500 |  | ASRAR AGA | ISSUED | Owner-led | Finishing Work in Progress | Rahma hussein sold to Asrar Aga
| 13 | 500 |  | EDAO HUSSEIN | ISSUED | Owner-led | Completed | Sold Via Amabassador Aman (1/5)
| 14 | 500 |  | BAME EDAO | ISSUED | Owner-led | Completed | Sold Via Amabassador Aman (2/5)
3 | 1 | 600 |  | MUSTEFA USMAN | ISSUED | Owner-led | Completed.Occupied | 100 Sq.M addition to the standard Plot Size.
| 2 | 500 |  | NESANET HAILU | PENDING | Owner-led | 1st Slab
| 3 | 500 |  | TIGIST G/EGZIYABEHER | ISSUED | Owner-led | Completed.Occupied | Gibril Kadi sold to current owner
| 4 | 500 |  | GEZAHEGN TESEMA | PENDING | Owner-led | G + 2 Partial Block Work, No Roof | Sileshi's Father
| 5 | 500 |  | SILESHI GEZAHEGN | PENDING | Owner-led | 1st Slab
| 6 | 500 |  | RAHMA HUSSEIN | NOT ISSUED | Owner-led | Elevation Column Errected | In House Sale
4 | 1 | 200 |  | ALEMAYEHU DAGNE ZEMARIAN
| 2 | 200 |  | HANA MELESE GIZAW
| 3 | 200 |  | GENET BIRHAN
| 4 | 200 |  | YARED GETAHUN
| 5 | 200 |  | MAMUSHET AREGAW
| 6 | 200 |  | DANIEL TESFA
| 7 | 200 |  | JENBERU TADESSE NADEW
| 8 | 200 |  | DR.DANIEL TEKLE G/EGZIABHER
| 9 | 200
| 10 | 200 |  | YOSEF MICHAEL AMBAYE
5 | 1 | 200 |  | ABERA ZEWEDU TESEMA
| 2 | 200 |  | DENNENESH GENANAW |  |  | Foundation Footings | The Client didn’t complete payment. Construction Cost is Unpaid
| 3 | 200 |  | GETU TEDLA AYELE
| 4 | 200 |  | DR. MEKURIA AREGAW
| 5 | 200 |  | SHEWANDAGNE SEIFU
| 6 | 200 |  | ROMAN SEIFU AND TED WONDAGEGNEH
| 7 | 200 |  | ETALEM DEMISE
| 8 | 200
| 9 | 200
| 10 | 200 |  | DANIEL SAMUEL NEGASH
| 11 | 200
| 12 | 200 |  | MEAZA W/MARIAM & GIRMA W/T
| 13 | 200 |  | BELETE DEMISEW W
| 14 | 200 |  | TULU DIMTU REAL ESTATE |  |  |  | A land parcel that was contested in court against GALGALO BORU, later solved in negotiation.
| 15 | 200 |  | ZEGEYE ABEBE & NIGISTE ASEFAW
| 16 | 200 |  | SIRAKE ZEWEDE & SABA ABREHAM
| 17 | 200 |  | HIRUT YIMERE/HAILU TADESSE
| 18 | 200 |  | ADDISALEM W/G.&YOSEF ALEME
6 | 1 | 200 |  | ESKEDAR MENGESHA |  |  |  | Construction Status is on Foundation Footings
| 2 | 200 |  | ZERIHUN MEKONNEN DAMTE
| 3 | 200 |  | GETENET TESHOME METAFERIA
| 4 | 200 |  | SELAMAWIT HABTE HAGOS
| 5 | 200 |  | MERUTSE GIRMAI & LEMLEM G/HIWOTE
| 6 | 200 |  | ROMAN ADMASU
| 7 | 200 |  | HABTAMU ASEFA
| 8 | 200 |  | MUNIRA ABDULLAHI
| 9 | 200 |  | HIRUT DERESE WOLDE
| 10 | 200 |  | AZEBE MOGESE
| 11 | 200 |  | MENBERE FIKADE
| 12 | 200 |  | ELENI TEKLE G/EGEZIHABERE
| 13 | 200 |  | GIRMA NEGASH & BETHLIHEM Z.
| 14 | 200 |  | ALEMAZ TECHANE
| 15 | 200 |  | REBECA G/HIWOT SOLOMON
| 16 | 200 |  | KEHASENA W/MIHRET
| 17 | 200 |  | EWNETU ABTE & HIRUT NIGATU
| 18 | 200 |  | NETSANET GIZAW &SEIFU W/YOHANES
7 | 1 | 200 |  | HALEWIYA OSMAN SEMERAI
| 2 | 200 |  | HIWOT ABEBE
| 3 | 200 |  | ABERA KIDANU HABTE
| 4 | 200 |  | SAMSON TESFAYE G/EGIZEYABHER
| 5 | 200 |  | GETACHEW VENERA GEMARI |  |  |  | Construction Status is on Foundation Footings
| 6 | 200 |  | ALMAW BIRU CHIKUALA
| 7 | 200 |  | GETACHEW ARAYA
| 8 | 200 |  | FEDILA MOHAMMED REDI
| 9 | 200 |  | MERID ADEMASU BEYENE
| 10 | 200 | [5 empty] | Construction Status is on Foundation Footings
| 11 | 200 |  | WELLELA HIRPHASA
| 12 | 200 |  | ALEMAZ ABERA MAMO
| 13 | 200 |  | SAADA ABDULLAHI ALI
| 14 | 200 |  | LEMELEM ALEMAYEHU
| 15 | 200 |  | AMIN JEMAL |  |  |  | Construction Status is on Foundation Footings
| 16 | 200 |  | FIKRE AMARE
| 17 | 200 |  | FITSUM KEBEDE
| 18 | 200 |  | ALISE PAROUNAKIAN YOHANESE
8 | 0 | 320 |  | TESHOME MEKETE | NOT ISSUED | Teshome | 1st Slabd | This is unidentified plot on DWG. Its built in Duplex natue
| 1 | 200 |  | MIHIRET SISAY
| 2 | 200 |  | MERAWI FELEKE AND JUDITH ABEBE
| 3 | 200 |  | DAMOZE GAMADA
| 4 | 200 |  | YOSEF YEREGA CHEGEN
| 5 | 200 |  | ABEBA TAFA
| 6 | 200 |  | MOLALET TSEDEKE W/GIORGIS
| 7 | 200 |  | SELAM DESTA KEBEDE |  |  |  | Construction Status is on Foundation Footings
| 8 | 200 |  | BIRUKTAWIT ABJE & KIRUBEL WENDOW.
| 9 | 200 |  | MARU DHABA
| 10 | 200 |  | MIHRET DEMISSEW |  |  |  | Dr. Mekuria. Undocmented sale
| 11 | 200 |  | TSEDALE MEKONEN &MESFIN MOTUMA
| 12 | 200 |  | BAYAN AHMED
| 13 | 200 |  | HIRUT G/SILASE | ISSUED |  |  | Construction Status is on Foundation Footings
| 14 | 200 |  | Tulu Dimtu Real Estate |  |  |  | Bare Land
| 15 | 200 |  | Tulu Dimtu Real Estate |  |  |  | Bare Land
| 16 | 200 |  | AHMED KADI | NOT ISSUED |  | Finishing Work in Progress
| 17 | 321 |  | Tulu Dimtu Real Estate (B*) |  |  |  | Bare Land
| 18 | 240 |  | Tulu Dimtu Real Estate (B*) |  |  |  | Bare Land
9 | 1 | 200 |  | ABDU KASIM |  |  | Completed
| 2 | 200 |  | HUZEYFA MUSA |  |  | Completed | No written Agreemnt
| 3 | 200 |  | SADAM AHMED |  |  | At Plastering Stage | Redwan's Brother
| 4 | 200 |  | FOZIYA AHMED |  |  | At Plastering Stage | Redwan's Sister
| 5 | 200 |  | DAWOD ALO |  |  | At Plastering Stage
| 6 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 7 | 200 |  | AYUB OR OBSA AKOSHA | ISSUED |  | Completed | Discprencies B/n Site and office report
| 8 | 200 |  | RIYAD | ISSUED |  | At Plastering Stage | Abduljelil Contractor Employee
| 9 | 200 |  | ??? |  |  | Elevation Column Errected | Redwan's Fatther In Law
| 10 | 370 |  | TULU DIMTU REAL ESTATE (B*) |  |  |  | Bare Land
| 11 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  |  | Bare Land
| 12 | 266 |  | TULU DIMTU REAL ESTATE (B*) |  |  |  | Bare Land
| 13 | 168 |  | TULU DIMTU REAL ESTATE (B*) |  |  |  | Bare Land
10 | 1 | 200 |  | HUSSEIN ABUBAKAR | ISSUED
2
| 3 |  |  | KHALID ABDULREZAK AMAN | NOT ISSUED |  |  | Sh/ Mohammed Nejib is the agent on the signed agreement
4
| 5 | 320 |  | REDWAN JEMAL IMAMU | ISSUED |  |  | Zahbiya Brother in law/ extension of few permiter on the river side.
11 | 1 | 200 |  | DESALEGN SISAY |  |  | Beasement + G + 1, Plastered | Raey Consultance
| 2 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 3 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 4 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 5 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 6 | 164 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 7 | 175 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 8 | 291 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 9 | 203 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
12 | 1 | 200 |  | SHEGAW NEGATU | ISSUED | Dereje | At Plastering Stage
| 2 | 200 |  | AGA | NOT ISSUED | Sherfedin | Block Work + Roof Work | Uncontracted Sale.
| 3 | 200 |  | MARKOS | ISSUED | Teshome | Block Work + Roof Work | Buyer is QATAR Resident
| 4 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 5 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 6 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 7 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 8 | 200 |  | TEWDROS | ISSUED | TABU | At Plastering Stage
| 9 | 200 |  | TIGIST DEREJE | ISSUED | Teshome | Finishing Work in Progress
| 10 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 11 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 12 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 13 | 274 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 14 | 184 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
13 | 1 | 200 |  | SEMIRA UMER | ISSUED | Sherfedin | At Plastering Stage
| 2 | 200 |  | ALAMUDIN KEDIR | ISSUED | Dereje | At Plastering Stage
| 3 | 200 |  | SADIK RAHMETO | ISSUED | TESHOME | Roof installed, Block Work in progress
| 4 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 5 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 6 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 7 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 8 | 200 |  | WORKU ABERA | ISSUED |  | At Plastering Stage
| 9 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 10 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 11 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 12 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 13 | 343 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 14 | 312 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
14 | 1 | 200 |  | ZEYTUNA ELIYASE | ISSUED | Dereje | Completed
| 2 | 200 |  | MERIA ELIYASE | ISSUED | Dereje | Completed
| 3 | 200 |  | RAMZIYA GULTA | ISSUED | Dereje | Completed. Occupied
| 4 | 200 |  | SEID IBRAHIM | NOT ISSUED | Dereje | Block Work + Roof Work
| 5 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 6 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 7 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 8 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 9 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 10 | 200 |  | KHALID MOHAMMED | ISSUED | Dereje | Completed
| 11 | 200 |  | ZUBEYDA KEDIR | ISSUED | Dereje | Completed
| 12 | 200 |  | MUDIN AHMED | ISSUED | Owner-led | At Plastering Stage | Daime (Abdulkerim Abduro) sold to current owner
| 13 | 200 |  | Tulu Dimtu Real Estate |  |  | Bare Land
| 14 | 200 |  | Tulu Dimtu Real Estate |  |  | Bare Land
| 15 | 200 |  | Tulu Dimtu Real Estate (B*) |  |  | Bare Land
| 16 | 200 |  | Tulu Dimtu Real Estate (B*) |  |  | Bare Land
| 17 | 308 |  | Tulu Dimtu Real Estate (B*) |  |  | Bare Land
15 | 1 | 200 |  | MESERET SHIMEKET | ISSUED | Dereje | Completed. Occupied
| 2 | 200 |  | FATIYA ABDU | ISSUED | Dereje | Completed
| 3 | 200 |  | SHIBELAY W/MARIAM | ISSUED | Dereje | Completed. Occupied
| 4 | 200 |  | SIDIKE ABA BULBUL | NOT ISSUED | Dereje | 1ST Slab
| 5 | 200 |  | MIFTAH | NOT ISSUED | Sherfedin | Block Work + Roof Work
| 6 | 200 |  | EMAN AWEL | NOT ISSUED | Dereje | Beasement + G + 1 | Awel Buseri
| 7 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 8 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 9 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 10 | 200 |  | NASRE HUSSEIN | ISSUED | Dereje | At Plastering Stage
| 11 | 200 |  | ABDU ABA MENCHA | ISSUED | Dereje | At Plastering Stage
| 12 | 200 |  | SADIYA ANEWAR | NOT ISSUED | Dereje | Foundation Work
| 13 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 14 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 15 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 16 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 17 | 296 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 18 | 264 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 19 | 145 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
16 | 1 | 200 |  | ELFENESH SHIFA | ISSUED | Sherfedin | Completed.Occupied | Previously allocated for Ahmed Jemal (Lawyer)
| 2 | 200 |  | YAKOB ADEM | ISSUED | Dereje | At Plastering Stage
| 3 | 200 |  | MULUGETA | ISSUED | Owner-led | At Plastering Stage | Khalid Mama sold to Bekele Ashebere, Bekele sold to current owner
| 4 | 200 |  | YAHYA ALIYI | ISSUED | Dereje | Completed | Yahaya sold it but title is not trasfered yet
| 5 | 200 |  | JUHAR BERDELO | ISSUED | Sherfedin | Completed.Occupied
| 6 | 200 |  | HAJI ALIYI HUSSEIN FATO | ISSUED | Sherfedin | Roof installed, Block Work incomplete
| 7 | 200 |  | RAHMET FARIS | NOT ISSUED | Sherfedin | On Top Tie Beam Work
| 8 | 200 |  | MUHABA AHMEDTEYIB | NOT ISSUED | Owner-led | Grade Beam | Abdulkerim Abduro
| 9 | 200 |  | MUHABA AHMEDTEYIB | NOT ISSUED | Owner-led | Grade Beam | Abdulkerim Abduro
| 10 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 11 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 12 | 200 |  | MESFIN ASERESE | NOT ISSUED | Sherfedin | Roof installed, Block Work in progress | Previously allocated for Alemayehu Tegegn (Lawyer)
| 13 | 200 |  | FEYSEL MAMA | PENDING | Owner-led | On Top Tie Beam, No Roof + No Block
| 14 | 200 |  | WUBET MAMA | PENDING | Owner-led | At Plastering Stage
| 15 | 200 |  | SEYFU MOHAMMED | NOT ISSUED | Dereje | Roof installed, Block Work incomplete
| 16 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 17 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 18 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 19 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 20 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 21 | 324 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 22 | 279 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
17 | 1 | 200 |  | NASREDIN ENDASHAW | ISSUED | Owner-led | Completed.Occupied
| 2 | 200 |  | ADEMEKACHEW | ISSUED | Owner-led | At Plastering Stage | Tekiya Abduqe (Woliyii Wife) sold to current owner
| 3 | 200 |  | MUNEWAR ZEYNEDIN | ISSUED | Owner-led | Completed.Occupied
| 4 | 200 |  | GIRMA TESHOME | ISSUED | Owner-led | Finishing Work in Progress
| 5 | 200 |  | SULTAN HEYREDIN | ISSUED | Owner-led | Completed.Occupied
| 6 | 240 |  | TOFIK NERSEBO | ISSUED | Owner-led | Finishing Work in Progress
| 7 | 200+ |  | TULU DIMTU REAL ESTATE | N/A |  |  | Bare land. Plot Size for these Plots are 200+
| 8 | 200+ |  | COMMUNITY CENTER | NOT ISSUED | Community | Beasement + 2nd Level slab | These parcel of land are set aside for the development of Religious Community Center
| 9 | 200+ |  | COMMUNITY CENTER
| 10 | 200 |  | YAHYA ALIYI | ISSUED | Dereje | Completed.Occupied
| 11 | 200 |  | MUSBEHA | ISSUED | Dereje | At Plastering Stage | Yahya Aliyi sold to current owner
| 12 | 200 |  | HUSSEIN ALIYI | ISSUED | Dereje | Completed.Occupied | Yahya Aliyi Brother
| 13 | 200 |  | RABIYA KEDIR | NOT ISSUED | Dereje | At Plastering Stage | A relative of Munira CBE NOOR Employee
| 14 | 200 |  | AMINAT MUSA | NOT ISSUED | Sherfedin | Block Work + Roof Work | Bare Land
| 15 | 200 |  | TULU DIMTU REAL ESTATE |  |  |  | Bare Land
| 16 | 200 |  | TULU DIMTU REAL ESTATE |  |  |  | Bare Land
| 17 | 200 |  | COMMUNITY CENTER | NOT ISSUED | Community | Beasement + 2nd Level slab | These parcel of land are set aside for the development of Religious Community Center
| 18 | 200 |  | COMMUNITY CENTER
| 19 | 200 |  | COMMUNITY CENTER
| 20 | 260 |  | COMMUNITY CENTER
| 21 | 192 |  |  |  |  | Bare Land
18 | 1 | 313 |  | TOFIK HULGAGA | ISSUED | Owner-led | Finishing Work in Progress
| 2 | 313 |  | NEJIB ABDUKU | ISSUED | Owner-led | Finishing Work in Progress
| 3 | 313 |  | SULEIMAN SEID OUSMAN | ISSUED | Owner-led | Finishing Work in Progress | Redwan Ahmed Sold to Current homeowner`
| 4 | 313 |  | ZENEBECH YAZE | ISSUED | Owner-led | Completed | Woliyi Guye Sold to Current homeowner
46A | 1 | 500 |  | ASIYA ABDELA & AHMED DEGDEBO | ISSUED | Owner-led | Finishing Work in Progress
| 2 | 500 |  | MOHAMMED DEGDABO | ISSUED | Owner-led | Completed. Move-in Ready | The Owner Rented the house to a school.
| 3 | 500 |  | FOZIYA AMAN | PENDING | Owner-led | At Plastering Stage | Previous Owner Foziya Aman Sold to Current Homeowner but Tittle is not transferred
| 4 | 500 |  | AYSHA BIYA | ISSUED | Owner-led | At Plastering Stage
| 5 | 500 |  | YASIN UMER | ISSUED | Owner-led | At Plastering Stage
| 6 | 500 |  | MOHAMMEDHUSSEIN ALIYI | ISSUED | Owner-led | At Plastering Stage
| 7 | 500 |  | SOFIYA TUSE | ISSUED | Owner-led | Completed. Move-in Ready
| 8 | 500 |  | MENTESENOT FEKERE | ISSUED | Owner-led | Completed. Occupied | Previous Owner Gibril Kadi Sold to Current Homeowner
47 | 1 | 500 |  | ZARO | ISSUED | Owner-led | Foundation Work | Purchase rate=50,000/ Currently Under Construction
| 2 | 500 |  | SHEKURE NASRE | ISSUED | Owner-led | Completed. Occupied
| 3 | 500 |  | ABRAR AGA | ISSUED | Owner-led | Completed. Occupied
| 4 | 500 |  | SISAY KENEDY | ISSUED | Owner-led | Finishing Work in Progress | Amir (Adama) sold to current homeowner
| 5 | 500 |  | AYSHA HUSSEN | ISSUED | Owner-led | At Plastering Stage | Mohammed Edao sold to Current owner/Sold Via Amabassador Aman (3/5)
| 6 | 500 |  | NASRO ABAS | ISSUED | Owner-led | At Plastering Stage | Sold Via Amabassador Aman (4/5)
| 7 | 500 |  | BURHAN HAJI ARSE | ISSUED | Owner-led | Completed. Occupied | Sold Via Amabassador Aman (5/5)
| 8 | 500 |  | MEZEGEBE ZELEKE | ISSUED | Owner-led | Completed. Occupied | Amir (Adama) sold to current homeowner
****************************************************************************************************************************************
Zone II G + 0
Block No. | Plot No. | Plot Size (Sq.M) | Built-up Area | Purchaser Name | Title Deeds Status | Contractor | Construction Status | Remark\Comments
19 | 1 | 405 |  | FOZIYA HUSSEIN (YAHYA ALIYI) | ISSUED | Dereje | Finishing Work in Progress | Sold to third party,but tittle is under the initial purchaser(Foziya)
| 2 | 285 |  | FOZIYA HUSSEIN (YAHYA ALIYI) | ISSUED | Dereje | Completed. Occupied | Sold to third party,but tittle is under the initial purchaser(Foziya)
| 3 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
20 | 1+2 | 471.6 |  | MOHAMMED IBRAHIM | ISSUED | Dereje | At Plastering Stage | The two plots are purchased by one customer; hence integrated as a single property. The land size specified on the deed is 390 SQ.Meter
21 | 1 | 200 |  | ADDISE SEID | ISSUED |  | Completed. Occupied
| 2 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Foundation Work/Floor Slab | Bare Land
| 3 | 200 |  | MUSEFA ABDELA | ISSUED | Dereje | Completed. Occupied
| 4 | 200 |  | TULU DIMTU REAL ESTATE |  | Sherfedin | Top tie Beam + Block Work
| 5 | 200 |  | YAHYA ALAMEREW | ISSUED | Dereje | Completed. Occupied | Previously, under Dereje Ayele(Contractor), later sold to the present owner
| 6 | 200 |  | ZEYENEBA RAHMETO | ISSUED | Sherfedin | Completed. Occupied
22 | 1 | 200 |  | MULUGETA DESALEGN | ISSUED | Sherfedin | Completed. Occupied
| 2 | 200 |  | TULU DIMTU REAL ESTATE |  | Sherfedin | StoneMason
| 3 | 200 |  | MUSTEFA H/HUSSEIN | ISSUED | Sherfedin | Block Work + Roof Work
| 4 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  |  | Bare Land
| 5 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  |  | Bare Land
| 6 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  |  | Bare Land
| 7 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  |  | Bare Land
| 8 | 230 |  | TULU DIMTU REAL ESTATE (B*) |  |  |  | Bare Land
| 9 | 200 |  | BETEKA MEKETE | ISSUED | Teshome | Block Work + Roof Work
| 10 | 200 |  | TESHOME MEKETE | ISSUED | Teshome | At Plastering Stage
| 11 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 12 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 13 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 14 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 15 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 16 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 17 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 18 | 324 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
23 | 1 | 320 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 2 | 200 |  | TIZITA | NOT ISSUED | Dereje | Finishing Work in Progress | Hailemichael(Finance) sold to the current tittle holder
| 3 | 200 |  | FERDOS OSMAN | ISSUED | Dereje | Occupied. At plastering Satge | Previously, under her deceased husband(Ali Mohammed, later court ruled for tittle transfer to her name.
| 4 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | StoneMason
| 5 | 200 |  | MOHAMMED ABDU | ISSUED | Dereje | Completed. Occupied
| 6 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 7 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 8 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 9 | 393 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 10 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 11 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 12 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 13 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
24 | 1 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 2 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 3 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 4 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 5 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 6 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 7 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 8 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 9 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 10 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 11 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 12 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 13 | 200 |  | HASSEN HUSSEIN | ISSUED | Sherfedin | Completed. Occupied
| 14 | 200 |  | MOHAMMED NURE | ISSUED | Sherfedin | At Plastering Stage
| 15 | 200 |  | BEDRU TEMAM | ISSUED | Sherfedin | Block Work + Roof Work
| 16 | 200 |  | ABAS ORMANO | ISSUED | Sherfedin | At Plastering Stage | Abas has already sold this land to third party, yet tittle is not transfered
25 | 1 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 2 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 3 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 4 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 5 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 6 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 7 | 200 |  | ABDULRAHMAN TAHIRO | NOT ISSUED | Sherfedin | Blockwork/ No Roofs
| 8 | 157 |  | TULU DIMTU REAL ESTATE (B*)
| 9 | 200 |  | MOHAMMED | ISSUED | Sherfedin | Completed. Occupied
| 10 | 200 |  | ESMAEL MUZE | ISSUED | Sherfedin | Completed. Occupied
| 11 | 200 |  | BARAKA NASIR | ISSUED | Sherfedin | Completed. Occupied
| 12 | 200 |  | AYUB REDI | NOT ISSUED | Sherfedin | Block Work + Roof Work
| 13 | 200 |  | TAJUDIN SHUKRI | ISSUED | Sherfedin | Block Work + Roof Work
| 14 | 200 |  | AHMED KEMAL | NOT ISSUED | Sherfedin | Completed. Occupied
| 15 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 16 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 17 | 180 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
26 | 1 | 200 |  | DEMEKECH BEGASHAW | NOT ISSUED | Dereje | On Top tie Beam
| 2 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 3 | 200 |  | MEKEDES GIRMA | NOT ISSUED | Dereje | At Plastering Stage
| 4 | 256 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 5 | 200 |  | RABIYA KEDIR | ISSUED | Sherfedin | Block Work + Roof Work
| 6 | 200 |  | RABIYA KEDIR | ISSUED | Sherfedin | Block Work + Roof Work
| 7 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 8 | 200 |  | SHEMSIYA | NOT ISSUED | Sherfedin | Block Work + Roof Work
| 9 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 10 | 333 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
27 | 1 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork/ No Roofs | Teshome's Contract (1/30)
| 2 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 3 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 4 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 5 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 6 | 200 |  | TOFIK SHIKUR | NOT ISSUED | Dereje | Roofwork Underway | Split-level house with a basement
| 7 | 200 |  | HANAN AKMEL | ISSUED | Dereje | At Plastering Stage | Abdulkerim Abduro sold this house to the current tittle holder
| 8 | 200 |  | ELIYASE AYELE | ISSUED | Dereje | Completed. Occupied | Dereje (Contractor) Brother; Split-level house with a basement
| 9 | 200 |  | TULU DIMTU REAL ESTATE |  |  | StoneMason
| 10 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 11 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 12 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 13 | 200 |  | ABDULMEJID MOHAMMED | NOT ISSUED | MOSH | Block Work + Roof Work
| 14 | 200 |  | NURU SETEGN | NOT ISSUED | MOSH | Block Work + Roof Work
| 15 | 200 |  | ABDULNEIM SHEMSU | ISSUED | Sherfedin | At Plastering Stage
| 16 | 200 |  | BEDRU MUZO | ISSUED | Sherfedin | Blockwork
28 | 1 | 200 |  | MOHAMMED DELSEBO | ISSUED | Sherfedin | At Plastering Stage
| 2 | 200 |  | MELIHA ASHREKA | ISSUED | Sherfedin | Block Work + Roof Work
| 3 | 200 |  | RABI MUZEYEN | ISSUED | Sherfedin | Block Work + Roof Work
| 4 | 200 |  | SEID KEYREDIN | PENDING | Sherfedin | At Plastering Stage
| 5 | 200 |  | BILAL DANUR | PENDING | Sherfedin | Block Work + Roof Work
| 6 | 200 |  | NUREDIN MOHAMMED | ISSUED | Sherfedin | Block Work + Roof Work
| 7 | 200 |  | KEDIR TURA | NOT ISSUED | Sherfedin | StoneMason
| 8 | 200 |  | HABIBA BILAL | NOT ISSUED | Sherfedin | Block Work + Roof Work
| 9 | 200 |  | DELIL DINO | ISSUED |  | Block Work + Roof Work
| 10 | 415 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 11 | 200 |  | SHEKURIA HUSSEIN ALI | ISSUED | Sherfedin | Block Work + Roof Work
| 12 | 200 |  | FEJREDIN KEDIR LALO |  | Sherfedin | Block Work + Roof Work
| 13 | 200 |  | AHMED ABDULKADIR |  | Sherfedin | Block Work + Roof Work
| 14 | 200 |  | RAHMET FARIS | ISSUED | Sherfedin | Block Work + Roof Work
| 15 | 200 |  | KERIMA JEMAL TEMAM | ISSUED | Sherfedin | Block Work + Roof Work
| 16 | 200 |  | KERIMA AMEL | NOT ISSUED | MOSH | Block Work + Roof Work
| 17 | 200 |  | ZEBIBA JEMAL | NOT ISSUED | MOSH | Block Work + Roof Work
| 18 | 200 |  | SEYFU YASIN | NOT ISSUED | Sherfedin | On Top tie Beam
| 19 | 200 |  | ESIHAK AKMEL |  | Sherfedin | On Top tie Beam
| 20 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 21 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 22 | 246 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
29 | 1 | 200 |  | FEDILA NUR | NOT ISSUED | Sherfedin | Block Work + Roof Work
| 2 | 200 |  | ANDINET SEID |  | Dereje | Cloumn Footings
| 3 | 200 |  | RAHMET | ISSUED | Sherfedin | Completed. Occupied
| 4 | 200 |  | ANISA AHMED | NOT ISSUED | Owner-led | On Top tie Beam | Abdulkerim Abduro sold this house to the current tittle holder
| 5 | 200 |  | ABUBAKAR AHMEDIN | ISSUED | Dereje | Completed. Occupied
| 6 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 7 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 8 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 9 | 191 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 10 | 200 |  | SEID MOHAMMED | ISSUED | Sherfedin | At Plastering Stage
| 11 | 200 |  | MERIAM | ISSUED | Sherfedin | At Plastering Stage
| 12 | 200 |  | JEMILA AHMED | NOT ISSUED | Sherfedin | At Plastering Stage
| 13 | 200 |  | ABDULSELAM FARIS | ISSUED | Sherfedin | At Plastering Stage
| 14 | 200 |  | SEID MOHAMMED | ISSUED | Sherfedin | At Plastering Stage
| 15 | 200 |  | ABDULFETA MOHAMMED | NOT ISSUED | Sherfedin | On Top tie Beam
| 16 | 200 |  | TOFIK ANEWAR | NOT ISSUED | MOSH | Block Work + Roof Work
| 17 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 18 | 280 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
30 | 1 | 200 |  | IBRAHIM KEMAL ABDELA | ISSUED | Dereje | NURU(GINIR) At Plastering Stage
| 2 | 200 |  | IBRAHIM KEMAL ABDELA | ISSUED | Dereje | NURU(GINIR) At Plastering Stage
| 3 | 200 |  | SOFIYA AHMED MUHE | ISSUED | Dereje | NURU(GINIR) At Plastering Stage
| 4 | 200 |  | SOFIYA AHMED MUHE | ISSUED | Dereje | NURU(GINIR) At Plastering Stage
| 5 | 200 |  | IBRAHIM KEMAL ABDELA | ISSUED | Dereje | NURU(GINIR) At Plastering Stage
| 6 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 7 | 248 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 8 | 200 |  | MOHAMMEDAMIN DEMEKE | NOT ISSUED | Dereje | At Plastering Stage
| 9 | 200 |  | ABDULNASIR SHEMSI | ISSUED | Dereje | Completed. Occupied
| 10 | 200 |  | JEMAL MOHAMMED | ISSUED | Dereje | Completed. Occupied
| 11 | 200 |  | ABDULRESHID ABDULLAHI | ISSUED | Dereje | Completed. Occupied
| 12 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 13 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 14 | 200 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 15 | 308 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
31 | 1 | 200 |  | FETIYA YUSUF BESHIR | ISSUED | Dereje | NURU(GINIR) At Plastering Stage
| 2 | 200 |  | SOFIYA AHMED MUHE | ISSUED | Dereje | NURU(GINIR) At Plastering Stage
| 3 | 200 |  | SOFIYA AHMED MUHE | ISSUED | Dereje | NURU(GINIR) At Plastering Stage
| 4 | 200 |  | IBRAHIM KEMAL ABDELA | ISSUED | Dereje | NURU(GINIR) At Plastering Stage
| 5 | 252 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
| 6 | 200 |  | BINIAM TEFERI | ISSUED | Dereje | At Plastering Stage
| 7 | 200 |  | EMAN MOHAMMED | ISSUED | Dereje | Completed. Occupied
| 8 | 200 |  | EMAN MOHAMMED | ISSUED | Dereje | Completed. Occupied
| 9 | 200 |  | FOZIYA HUSSEIN (YAHYA ALIYI) | ISSUED | Dereje | At Plastering Stage
| 10 | 200 |  | FOZIYA HUSSEIN (YAHYA ALIYI) | ISSUED | Dereje | At Plastering Stage
| 11 | 216 |  | TULU DIMTU REAL ESTATE (B*) |  |  | Bare Land
32 | 1 | 200 |  | BIRHANE DESALEGN | ISSUED | Owner-led | Completed. Occupied
| 2 | 200 |  | BEYENE TILAHUN | ISSUED | Owner-led | Completed. Occupied | He is a pastor
| 3 | 200 |  | FEKERE WOLDEMARIAM | ISSUED | Owner-led | Completed. Occupied
| 4 | 200 |  | ********** | ISSUED | Owner-led | At Plastering Stage
| 5 | 200 |  | ********** | ISSUED | Owner-led | Completed. Occupied
| 6 | 200 |  | TAMERAT | ISSUED | Owner-led | Completed. Occupied
| 7 | 200 |  | MIMI | ISSUED | Owner-led | Completed. Occupied
| 8 | 200 |  | TSEGAYE DESEBALEW | ISSUED | Owner-led | Completed. Occupied
| 9 | 200 |  | ALEMAZ HAILE | ISSUED | Owner-led | Completed. Occupied
| 10 | 200 |  | ********** | ISSUED | Owner-led | Completed. Occupied
| 11 | 200 |  | EWENET TEBEBE | ISSUED | Owner-led | Completed. Occupied
| 12 | 200 |  | SEBESEB | ISSUED | Owner-led | Completed. Occupied
| 13 | 200 |  | ENDALE HAILE | ISSUED | Owner-led | Completed. Occupied
| 14 | 200 |  | SOFIA AHMED | ISSUED | Owner-led | Completed. Occupied | Sofiya bought it from Girma/ A house with an attached kiosk
33 | 1 | 259 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 2 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 3 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 4 | 200 |  | ASEGEDE NEGASH | ISSUED | Owner-led | Completed. Occupied | VIA TAMERE
| 5 | 200 |  | ********** | ISSUED | Owner-led | Completed. Occupied | The current owner bought it from Lema Tsegaye/VIA TAMERE
| 6 | 200 |  | NASIR | ISSUED | Owner-led | Completed. Occupied | Bought it from Tamere beri
| 7 | 200 |  | MEAREGE ASEFAW | ISSUED | Owner-led | Completed. Occupied | Bought it from Tsion Wolde/VIA TAMERE
| 8 | 202 |  | KEMZU DEGEFE | NOT ISSUED | MOSH | Block Work + Roof Work
| 9 | 200 |  | ABDULKAIF ANEWAR | NOT ISSUED | MOSH | Block Work + Roof Work
| 10 | 200 |  | SOLOMON TEFERA | NOT ISSUED | Sherfedin | On Top tie Beam
| 11 | 200 |  | FREHIWOT EJIGU | ISSUED | MOSH | At Plastering Stage
| 12 | 200 |  | TADESSE | ISSUED | Sherfedin | Completed. Occupied
| 13 | 200 |  | LEMA TSEGAYE | ISSUED | Owner-led | Completed. Occupied | VIA TAMERE
| 14 | 200 |  | MESKEREM ABEBE | ISSUED | Owner-led | Completed. Occupied | VIA TAMERE
34 | 1 | 338 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 2 | 300 |  | FREZER DEBEBE | ISSUED | Owner-led | At Plastering Stage | G + 2 House
| 3 | 300 |  | FEVEN ESHETU | ISSUED | Owner-led | Completed. Occupied | Aboyneh/G + 1 House
| 4 | 310 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 5 | 336 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 6 | 278 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 7 | 200 |  | DOYO | NOT ISSUED | A/Majid M | Foundation Work/StoneMason | DOYO (1/13)
| 8 | 200 |  | SEADA MIFTHA BILAL | NOT ISSUED | A/Majid M | Foundation Work/StoneMason | DOYO (2/13)
| 9 | 200 |  | ABDULKADIR BILAL | NOT ISSUED | A/Majid M | Foundation Work/StoneMason | DOYO (3/13)
| 10 | 200 |  | MOHAMMED SHEREFA | NOT ISSUED | A/Majid M | Foundation Work/StoneMason | DOYO (4/13)
| 11 | 200 |  | MURGU SIBANI AYGUDO | NOT ISSUED | A/Majid M | Foundation Work/StoneMason | DOYO (5/13)
| 12 | 200 |  | MIFTHA BILAL | NOT ISSUED | A/Majid M | Foundation Work/StoneMason | DOYO (6/13)
36 | 1 | 180 |  | BADHADHA GUTA | NOT ISSUED | Sherfedin | Block Work + Roof Work
| 2 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork/ No roofs | Teshome's Contract (2/30)
| 3 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Block Work + Roof Work | Teshome's Contract (3/30)
| 4 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork/ No roofs | Teshome's Contract (4/30)
| 5 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork/ No roofs | Teshome's Contract (5/30)
| 6 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork/ No roofs | Teshome's Contract (6/30)
| 7 | 400 |  | TSEGA BEZU GETACHEW |  | Owner-led | completed | Owner make use of the property for Church service
| 8 | 347 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork/ No roofs | Teshome's Contract (7/30)
| 9 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork/ No roofs | Teshome's Contract (8/30)
| 10 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork/ No roofs | Teshome's Contract (9/30)
| 11 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork/ No roofs | Teshome's Contract (10/30)
| 12 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork/ No roofs | Teshome's Contract (11/30)
| 13 | 254 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
37 | 1 | 283 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 2 | 215 |  | TULU DIMTU REAL ESTATE |  | Dereje | Partial Stonemason
| 3 | 247 |  | TULU DIMTU REAL ESTATE |  | Dereje | Stonemason
| 4 | 276 |  | TULU DIMTU REAL ESTATE |  | Dereje | Stonemason
| 5 | 307 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork + Roofing | Teshome's Contract (12/30)
| 6 | 177 |  | TULU DIMTU REAL ESTATE |  | Dereje | Stonemason
| 7 | 177 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork + Roofing | Teshome's Contract (13/30)
38 | 1 | 200 |  | HELEN DEREJE | ISSUED | Teshome | At Plastering Stage | Teshome's Contract (14/30)
| 2 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork + Roofing | Teshome's Contract (15/30)
| 3 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Stonemason
| 4 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Stonemason
| 5 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Stonemason
| 6 | 200 |  | TIGIST DEREJE & HELEN DEREJE | ISSUED | Teshome | Blockwork + Roofing | Teshome's Contract (16/30)
| 7 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork + Roofing | Teshome's Contract (17/30)
| 8 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Stonemason
| 9 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Stonemason
| 10 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Stonemason
| 11 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork + Roofing | Teshome's Contract (18/30)
| 12 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork + Roofing | Teshome's Contract (19/30)
| 13 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork + Roofing | Teshome's Contract (20/30)
39 | 1 | 228 |  | KENZU MIFTHA BILAL | NOT ISSUED | A/Majid M | Bare Land | DOYO (7/13)
| 2 | 200 |  | SARA RAHMETO MUZEYIN | NOT ISSUED | A/Majid M | Bare Land | DOYO (8/13)
| 3 | 200 |  | HAYAT JEMAL BEDAWI | NOT ISSUED | A/Majid M | Bare Land | DOYO (9/13)
| 4 | 200 |  | SISAY WOLDESEMAYAT | ISSUED | Owner-led | Completed. Occupied | There is an existing G+1 house on this plot/Occupied by the homeowner
| 5 | 200 |  | JOHNNY TEFERA | ISSUED | Owner-led | Beasement + Ground Level | Basement level is occupied. Ground floor column footings
| 6 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork + Roofing | Teshome's Contract (21/30)
| 7 | 325 |  | ALI MOHAMMED | NOT ISSUED | Teshome | Blockwork + Roofing | Teshome's Contract (22/30)
| 8 | 200 |  | HIWOT TSEGAYE | ISSUED | Owner-led | Completed | There is an existing G+2 house on this plot/Occupied by the homeowner
| 9 | 200 |  | KEDIR NASIR DESTA | NOT ISSUED | A/Majid M | Bare Land | DOYO (10/13)
| 10 | 200 |  | MUBAREK MIFTHA BILAL | NOT ISSUED | A/Majid M | Bare Land | DOYO (11/13)
| 11 | 200 |  | NEIMA MIFTHA BILAL | NOT ISSUED | A/Majid M | Bare Land | DOYO (12/13)
| 12 | 200 |  | KEDRIYA JEMAL BESHIR | NOT ISSUED | A/Majid M | Bare Land | DOYO (13/13)
| 13 | 274 |  | MARKOS MERGA BATU | NOT ISSUED | Owner-led | Plastered. Basement + G + 1 | There is an existing G+1 house on this plot/Occupied by the homeowner
| 14 | 240 |  | GERMACHEW BEKELE | NOT ISSUED | Owner-led | G + 1/Basement/slab + Roof | There is an existing G+1 house on this plot/Occupied by the homeowner
40 | 1 | 200 |  | SAMUEL ABEBE | ISSUED | Owner-led | Completed. Occupied | VIA TAMERE
| 2 | 200 |  | HAILE GABRIEL WOLDE | ISSUED | Owner-led | Completed. Occupied | Occupied
| 3 | 226 |  | SHAFI KAMIL | ISSUED | Owner-led | Completed | Shafi sold to current owner but tittle not transferred /Teshome's Contract (23/30)
| 4 | 226 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork + Roofing | Teshome's Contract (24/30)
| 5 | 226 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork + Roofing | Teshome's Contract (25/30)
| 6 | 226 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork + Roofing | Teshome's Contract (26/30)
| 7 | 226 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork + Roofing | Teshome's Contract (27/30)
| 8 | 200 |  | Under Review |  |  | Stonemason | An ownership claim from third party. No evidence of tittle is provided (1/3)
| 9 | 200 |  | AWEL ABA BORU | ISSUED | Owner-led | Completed. Occupied
| 10 | 200 |  | YEDENEKACHEW SHEWAREGA | ISSUED | Owner-led | Completed. Occupied
| 11 | 246 |  | FREHIWOT WOLDESELASE | ISSUED | Owner-led | Completed. Occupied | Teshome's Contract (28/30)
| 12 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork + Roofing | Teshome's Contract (29/30)
| 13 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Blockwork + Roofing | Teshome's Contract (30/30)
| 14 | 200 |  | MERGA BATU | NOT ISSUED | Owner-led | Completed. Occupied
41 | 1 | 200 |  | WAKE | NOT ISSUED | Sherfedin | Blockwork without top tie beam
| 2 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Elevation Columns Errected
| 3 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Elevation Columns Errected
| 4 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Elevation Columns Errected
| 5 | 400 |  | TULU DIMTU REAL ESTATE |  | Teshome | StoneMason
| 6 | 200 |  | ALIYA ABDELA | ISSUED | Dereje | At Plastering Stage
| 7 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Elevation Columns Errected
| 8 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Elevation Columns Errected
| 9 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Elevation Columns Errected
| 10 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Elevation Columns Errected
| 11 | 200 |  | TULU DIMTU REAL ESTATE |  | Dereje | Elevation Columns Errected
| 12 | 200 |  | TULU DIMTU REAL ESTATE |  | Teshome | Elevation Columns Errected
42 | 1 | 300 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 2 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 3 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 4 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 5 | 200 |  | MUDIN | ISSUED | Dereje | At Plastering Stage
| 6 | 302 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 7 | 200 |  | TULU DIMTU REAL ESTATE |  |  | Bare Land
| 8 | 200 |  | HASSEN IBRAHIM | ISSUED | Dereje | Completed. Occupied
| 9 | 200 |  | DEREJE AYELE | NOT ISSUED | Dereje | Completed. Occupied
| 10 | 200 |  | TADIYOS | ISSUED | Dereje | Completed. Occupied
43 | 1 | 300 |  | SAUDA BEZAW | ISSUED | Owner-led | Completed. Occupied | Sauda bought it from sadike
| 2 | 200 |  | SULTAN IBRAHIM | ISSUED | Owner-led | Completed. Occupied
| 3 | 200 |  | SEMERETE ASHENAFI | ISSUED | Owner-led | Completed. Occupied
| 4 | 200 |  | MOHAMMED | ISSUED | Owner-led | Completed. Occupied
| 5 | 200 |  | AZEBE BIRHANE | ISSUED | Owner-led | At Plastering Stage | Amongst the 5 plots which was under review
| 6 | 200 |  | ALEMAZ KEMAL | ISSUED | Owner-led | Completed. Occupied | Tittle is yet to be transferred from the previous house buyer
| 7 | 300 |  | SADIKE | ISSUED | Owner-led | Completed. Occupied
| 8 | 200 |  | KIFELE | ISSUED | Owner-led | Completed. Occupied
| 9 | 200 |  | ALEMAZ BEYENE | ISSUED | Owner-led | Completed. Occupied
| 10 | 200 |  | ASECHALEW ENDALE | ISSUED | Owner-led | Completed. Occupied
| 11 | 200 |  | DEBEBE GOBENA | ISSUED | Owner-led | Completed. Occupied
| 12 | 200 |  | SOSINA ABEBE | ISSUED | Owner-led | Completed. Occupied
44 | 1 | 200 |  | Under Review |  |  | Stonemason | An ownership claim from third party. Evidence of tittle is provided (2/3)
| 2 | 200 |  | MULUGETA KASSA | ISSUED | Owner-led | At Plastering Stage/Occupied
| 3 | 200 |  | ATAKELETI | ISSUED | Owner-led | Completed. Occupied
| 4 | 200 |  | FREZER | ISSUED | Owner-led | Completed. Occupied
| 5 | 200 |  | AYELE | ISSUED | Owner-led | Completed. Occupied
| 6 | 200 |  | BAYEHUSH NEGESU | ISSUED | Owner-led | Completed. Occupied | Zenabu the primary owner, sold to Bayehush
| 7 | 300 |  | ABEBECH TESEMA | ISSUED | Owner-led | Completed. Occupied | Daniel Bashir (OilLibya), sold to current owner
| 8 | 200 |  | AMANUEL YELMA | ISSUED | Owner-led | Completed. Occupied
| 9 | 200 |  | ESKEDAR | ISSUED | Owner-led | Completed. Occupied | G + 2 House
| 10 | 200 |  | Under Review |  |  | Stonemason | An ownership claim from third party. Evidence of tittle is provided (3/3)
| 11 | 200 |  | MEBRATE BEKELE | ISSUED | Owner-led | Completed. Occupied
| 12 | 200 |  | MEBRATE BEKELE | ISSUED | Owner-led | Completed. Occupied
| 13 | 200 |  | DEMESE WOLDE YOHANESS | ISSUED | Owner-led | Completed. Occupied | Zeleke sold to Demese
| 14 | 300 |  | WUBE ALEM ASEFA | ISSUED | Owner-led | Completed. Occupied | Daniel Bashir (OilLibya), sold to current owner
45 | 1 | 200 |  | NURI HUSSEIN | ISSUED | Owner-led | Completed. Occupied
| 2 | 200 |  | TSEGAYE SHEWAYE | ISSUED | Owner-led | Completed. Occupied
| 3 | 200 |  | BEHARU FISEHA | ISSUED | Owner-led | Completed. Occupied
| 4 | 200 |  | NAZERAWIT KASSA | ISSUED | Owner-led | Block work + Roof work | Amongst the 5 plots which was under review
| 5 | 200 |  | CHERE | ISSUED | Owner-led | Completed. Occupied | Chere the current tittle holder bought it from initial contract holder with Tulu Dimtu
| 6 | 200 |  | GETACHEW ASAYE | ISSUED | Owner-led | Completed. Occupied
| 7 | 300 |  | HIWOTE MEZEGEBE | ISSUED | Owner-led | Completed. Occupied | Tesfaye (OilLibya), sold to Hiwote
| 8 | 200 |  | ZELALEM CHEFE | ISSUED | Owner-led | Completed. Occupied | Initial homebuyer Worku, sold to Zelalem
| 9 | 200 |  | MOHAMMED DEDEGEBO | ISSUED | Owner-led | Completed. Occupied
| 10 | 200 |  | ZELALEM KEBEDE | ISSUED | Owner-led | Completed. Occupied | Bought it from Neku Fersha
| 11 | 200 |  | MEKEBEBE G/MESKEL | ISSUED | Owner-led | Completed. Occupied
| 12 | 200 |  | HIWOTE MEZEGEBE | ISSUED | Owner-led | Completed. Occupied
| 13 | 200 |  | KA'ELAY ABREHA | ISSUED | Owner-led | Completed. Occupied
| 14 | 300 |  | ************** | ISSUED | Owner-led | On Top Tie Beam | Tesfaye (OilLibya), sold to Hiwote
46B | 1 | 348 |  | Tulu Dimtu Real Estate (B*) |  |  |  | Bare Land
| 2 | 386 |  | Tulu Dimtu Real Estate (B*) |  |  | Stonemason
| 3 | 214 |  | Tulu Dimtu Real Estate (B*) |  |  | Stonemason
| 4 | 200 |  | Yahya Aliyi |  |  | Plastered
| 5 | 177 |  | Tulu Dimtu Real Estate (B*) |  |  |  | Bare Land

## Sheet3
|  |  | Dereje |  | Uncontracted Sale.
| NURU |  | Dereje |  | Uncontracted Sale.
| YAHYA ALIYI |  | Dereje
| ABDULJEBAR HUSSEN |  | Dereje
TAYECH BETEWEDED
NEJAT MOHAMMED
ASEFA HUNDE
EDRIS GIBRIL
| SHEMSIYA AHMED |  |  |  | Ahmed Tusa
| YAHYA ALIYI |  |  |  | Yahya's Residence
| MESERET TAFESE |  |  | Completed | Rahma hussein sold to Bekele Ashabir, Bekele sold to current owner
| ASRAR AGA |  |  |  | Rahma hussein sold to Asrar Aga
| EDAO HUSSEIN |  |  | Completed
| BAME EDAO |  |  | Completed
MUSTEFA USMAN
| NESANET HAILU | PENDING |  | 1st Slab
| TIGIST G/EGZIYABEHER |  |  |  | Gibril Kadi sold to current owner
| GEZAHEGN TESEMA | PENDING |  | G + 2 Partial Block Work, No Roof | Sileshi's Father
| SILESHI GEZAHEGN | PENDING |  | 1st Slab
| RAHMA HUSSEIN |  |  | Elevation Column Errected | In House Sale
ALEMAYEHU DAGNE ZEMARIAN
HANA MELESE GIZAW
GENET BIRHAN
YARED GETAHUN
MAMUSHET AREGAW
DANIEL TESFA
JENBERU TADESSE NADEW
DR.DANIEL TEKLE G/EGZIABHER
YOSEF MICHAEL AMBAYE
ABERA ZEWEDU TESEMA
DENNENESH GENANAW
GETU TEDLA AYELE
DR. MEKURIA AREGAW
SHEWANDAGNE SEIFU
ROMAN SEIFU AND TED WONDAGEGNEH
ETALEM DEMISE
DANIEL SAMUEL NEGASH
MEAZA W/MARIAM & GIRMA W/T
BELETE DEMISEW W
| TULU DIMTU REAL ESTATE |  |  |  | A land parcel that was contested in court against GALGALO BORU, later solved in negotiation.
ZEGEYE ABEBE & NIGISTE ASEFAW
SIRAKE ZEWEDE & SABA ABREHAM
HIRUT YIMERE/HAILU TADESSE
ADDISALEM W/G.&YOSEF ALEME
ESKEDAR MENGESHA
ZERIHUN MEKONNEN DAMTE
GETENET TESHOME METAFERIA
SELAMAWIT HABTE HAGOS
MERUTSE GIRMAI & LEMLEM G/HIWOTE
ROMAN ADMASU
HABTAMU ASEFA
MUNIRA ABDULLAHI
HIRUT DERESE WOLDE
AZEBE MOGESE
MENBERE FIKADE
ELENI TEKLE G/EGEZIHABERE
GIRMA NEGASH & BETHLIHEM Z.
ALEMAZ TECHANE
REBECA G/HIWOT SOLOMON
KEHASENA W/MIHRET
EWNETU ABTE & HIRUT NIGATU
NETSANET GIZAW &SEIFU W/YOHANES
HALEWIYA OSMAN SEMERAI
HIWOT ABEBE
ABERA KIDANU HABTE
SAMSON TESFAYE G/EGIZEYABHER
GETACHEW VENERA GEMARI
ALMAW BIRU CHIKUALA
GETACHEW ARAYA
FEDILA MOHAMMED REDI
MERID ADEMASU BEYENE
WELLELA HIRPHASA
ALEMAZ ABERA MAMO
SAADA ABDULLAHI ALI
LEMELEM ALEMAYEHU
AMIN JEMAL
FIKRE AMARE
FITSUM KEBEDE
ALISE PAROUNAKIAN YOHANESE
| TESHOME MEKETE |  | Teshome | 1st Slabd
MIHIRET SISAY
MERAWI FELEKE AND JUDITH ABEBE
DAMOZE GAMADA
YOSEF YEREGA CHEGEN
ABEBA TAFA
MOLALET TSEDEKE W/GIORGIS
SELAM DESTA KEBEDE
BIRUKTAWIT ABJE & KIRUBEL WENDOW.
MARU DHABA
| MIHRET DEMISSEW |  |  |  | Dr. Mekuria. Undocmented sale
TSEDALE MEKONEN &MESFIN MOTUMA
BAYAN AHMED
| HIRUT G/SILASE | ISSUED
AHMED KADI
| ABDU KASIM |  |  | Completed
| HUZEYFA MUSA |  |  | Completed
SADAM AHMED
FOZIYA AHMED
DAWOD ALO
TULU DIMTU REAL ESTATE
| AYUB OR OBSA AKOSHA | ISSUED |  | Completed
| RIYAD | ISSUED |  |  | Abduljelil Contractor Employee
Elevation Column Errected
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
200 | HUSSEIN ABUBAKAR | ISSUED
| KHALID ABDULREZAK AMAN |  |  |  | Sh/ Mohammed Nejib is the agent on the signed agreement
320 | REDWAN JEMAL IMAMU | ISSUED |  |  | Zahbiya Brother in law/ extension of few permiter on the river side.
| DESALEGN SISAY |  |  | Beasement + G + 1, Plastered | Raey Consultance
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
| SHEGAW NEGATU |  | Dereje
| AGA |  | Sherfedin |  | Uncontracted Sale.
| MARKOS |  | Teshome |  | Buyer is QATAR Resident
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
| TEWDROS |  | TABU
| TIGIST DEREJE |  | Teshome
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
| SEMIRA UMER |  | Sherfedin
| ALAMUDIN KEDIR |  | Dereje
| SADIK RAHMETO |  | TESHOME
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
WORKU ABERA
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
| ZEYTUNA ELIYASE |  | Dereje | Completed
| MERIA ELIYASE |  | Dereje | Completed
| RAMZIYA GULTA |  | Dereje | Completed. Occupied
| SEID IBRAHIM |  | Dereje
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
| KHALID MOHAMMED |  | Dereje | Completed
| ZUBEYDA KEDIR |  | Dereje | Completed
| MUDIN AHMED |  |  |  | Daime (Abdulkerim Abduro) sold to current owner
| MESERET SHIMEKET |  | Dereje | Completed. Occupied
| FATIYA ABDU |  | Dereje | Completed
| SHIBELAY W/MARIAM |  | Dereje | Completed. Occupied
| SIDIKE ABA BULBUL |  | Dereje | 1ST Slab
| MIFTAH |  | Sherfedin
| EMAN AWEL |  | Dereje | Beasement + G + 1 | Awel Buseri
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
| NASRE HUSSEIN |  | Dereje
| ABDU ABA MENCHA |  | Dereje | At Plastering Stage
| SADIYA ANEWAR |  | Dereje | Foundation Work
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
| NASREDIN ENDASHAW |  | Owner-led | Completed.Occupied
| ADEMEKACHEW |  | Owner-led |  | Tekiya Abduqe (Woliyii Wife) sold to current owner
| MUNEWAR ZEYNEDIN |  | Owner-led | Completed.Occupied
| GIRMA TESHOME |  | Owner-led
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
| TOFIK HULGAGA |  | Owner-led
| NEJIB ABDUKU |  | Owner-led
Owner-led
| ZENEBECH YAZE |  | Owner-led | Completed | Woliyi Guye Sold to Current homeowner
| ASIYA ABDELA & AHMED DEGDEBO |  | Owner-led
| MOHAMMED DEGDABO |  | Owner-led
| FOZIYA AMAN |  | Owner-led
| AYSHA BIYA |  | Owner-led
| YASIN UMER |  | Owner-led
| MOHAMMEDHUSSEIN ALIYI |  | Owner-led
| SOFIYA TUSE |  | Owner-led
| MENTESENOT FEKERE |  | Owner-led | Completed. Occupied | Previous Owner Gibril Kadi Sold to Current Homeowner
| ZARO |  | Owner-led | Foundation Work | Purchase rate=50,000/ Currently Under Construction
| SHEKURE NASRE |  | Owner-led | Completed. Occupied
| ABRAR AGA |  | Owner-led | Completed. Occupied
| SISAY KENEDY |  | Owner-led |  | Amir (Adama) sold to current homeowner
| AYSHA HUSSEN |  | Owner-led |  | Mohammed Edao sold to Current owner/Sold Via Amabassador Aman (3/5)
| NASRO ABAS |  | Owner-led
| BURHAN HAJI ARSE |  | Owner-led | Completed. Occupied
| MEZEGEBE ZELEKE |  | Owner-led | Completed. Occupied | Amir (Adama) sold to current homeowner
| FOZIYA HUSSEIN (YAHYA ALIYI) |  | Dereje |  | Sold to third party,but tittle is under the initial purchaser(Foziya)
| FOZIYA HUSSEIN (YAHYA ALIYI) |  | Dereje | Completed. Occupied | Sold to third party,but tittle is under the initial purchaser(Foziya)
TULU DIMTU REAL ESTATE
| MOHAMMED IBRAHIM |  | Dereje |  | The two plots are purchased by one customer; hence integrated as a single property. The land size specified on the deed is 390 SQ.Meter
| ADDISE SEID |  |  | Completed. Occupied
| TULU DIMTU REAL ESTATE |  | Dereje | Foundation Work/Floor Slab
| MUSEFA ABDELA |  | Dereje | Completed. Occupied
| TULU DIMTU REAL ESTATE |  | Sherfedin | Top tie Beam + Block Work
| YAHYA ALAMEREW |  | Dereje | Completed. Occupied | Previously, under Dereje Ayele(Contractor), later sold to the present owner
| ZEYENEBA RAHMETO |  | Sherfedin | Completed. Occupied
| MULUGETA DESALEGN |  | Sherfedin | Completed. Occupied
| TULU DIMTU REAL ESTATE |  | Sherfedin
| MUSTEFA H/HUSSEIN |  | Sherfedin
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
| BETEKA MEKETE |  | Teshome
| TESHOME MEKETE | ISSUED | Teshome
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE
| TIZITA |  | Dereje |  | Hailemichael(Finance) sold to the current tittle holder
| FERDOS OSMAN | ISSUED | Dereje | Occupied. At plastering Satge | Previously, under her deceased husband(Ali Mohammed, later court ruled for tittle transfer to her name.
| TULU DIMTU REAL ESTATE |  | Dereje
| MOHAMMED ABDU | ISSUED | Dereje | Completed. Occupied
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
| HASSEN HUSSEIN | ISSUED | Sherfedin | Completed. Occupied
| MOHAMMED NURE | ISSUED | Sherfedin
| BEDRU TEMAM | ISSUED | Sherfedin
| ABAS ORMANO | ISSUED | Sherfedin |  | Abas has already sold this land to third party, yet tittle is not transfered
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
| ABDULRAHMAN TAHIRO |  | Sherfedin
TULU DIMTU REAL ESTATE (B*)
| MOHAMMED | ISSUED | Sherfedin | Completed. Occupied
| ESMAEL MUZE | ISSUED | Sherfedin | Completed. Occupied
| BARAKA NASIR | ISSUED | Sherfedin | Completed. Occupied
| AYUB REDI |  | Sherfedin
| TAJUDIN SHUKRI | ISSUED | Sherfedin
| AHMED KEMAL |  | Sherfedin | Completed. Occupied
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
| DAMENECH BEGASHA |  | Dereje | On Top tie Beam
TULU DIMTU REAL ESTATE
| MEKEDES GIRMA |  | Dereje
TULU DIMTU REAL ESTATE (B*)
| RABIYA KEDIR | ISSUED | Sherfedin
| RABIYA KEDIR | ISSUED | Sherfedin
TULU DIMTU REAL ESTATE
| SHEMSIYA |  | Sherfedin
TULU DIMTU REAL ESTATE (B*)
TULU DIMTU REAL ESTATE (B*)
| TULU DIMTU REAL ESTATE |  | Teshome
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
| TOFIK SHIKUR |  | Dereje | Roofwork Underway | Split-level house with a basement
| HANAN AKMEL | ISSUED | Dereje |  | Abdulkerim Abduro sold this house to the current tittle holder
| ELIYASE AYELE | ISSUED | Dereje | Completed. Occupied | Dereje (Contractor) Brother; Split-level house with a basement
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
TULU DIMTU REAL ESTATE
| ABDULMEJID MOHAMMED |  | MOSH
| NURU SETEGN |  | MOSH
| ABDULNEIM SHEMSU | ISSUED | Sherfedin
| BEDRU MUZO | ISSUED | Sherfedin
| MOHAMMED DELSEBO | ISSUED | Sherfedin
| MELIYA ASHREKA |  | Sherfedin
| RABI MUZEYEN | ISSUED | Sherfedin
| SEID KEYREDIN |  | Sherfedin
| BILAL DANUR |  | Sherfedin
| NUREDIN MOHAMMED | ISSUED | Sherfedin
| KEDIR TURA |  | Sherfedin
| HABIBA BILAL |  | Sherfedin
DELIL DINO
TULU DIMTU REAL ESTATE (B*)